## Ashish
# | Date | Module | Screen | Issue | Status | Notes
1 | 2025-03-17 | Client | Add client | Validation message not showing next to the field name | Pending
2 | 2025-03-17 | Client | Listing | Action menu is not propely visible for list bottom items | Pending

## sudharshan
# | Date | Module | Screen | Issue | Status | Notes
1 | 2025-03-17 | Client | setting,profile | In Basic info we can't upload an image | complete
2 | 2025-03-17 | Client | scheduled | In schedule report the closing icon not proper visible | pending
3 | 2025-03-17 | My expenses | My expenses | In Expenses details if we add a new item the '+' symbol show twice | complete
4 | 2025-03-17 | My expenses | My expenses | After created Expenses the ellipsis icon (more option) not proper visible | complete
5 | 2025-03-17 | Tasks | Listing | Action menu is not propely visible for list bottom items | Complete
6 | 2025-03-17 | Home | Home | Wrong number of all tasks | complete
7 | 2025-03-17 | Home | Home | this month option is not working | Complete
8 | 2025-03-17 | Department | listing | Action menu is not propely visible for list bottom items | complete
9 | 2025-03-17 | Department | Add Department | we can make unnecessary kind of department no restriction | complete
10 | 2025-03-17 | Client | clients | We can add more sort by properties | pending
11 | 2025-03-17 | department | department | after clicking checkbox. we cann't perform any action "No using" | complete
12 | 2025-03-17 | projects | Add projects | Validation message not showing next to the field name | complete
13 | 2025-03-17 | projects | Projects | Checkbox is working | complete
14 | 2025-03-17 | Employee | Listing | Action menu is not propely visible for list bottom items | complete
15 | 2025-03-17 | Employee | Add employee | Validation message not showing next to the field name | complete
16 | 2025-03-17 | Workspaces | Successful Message | After submitting it's successful message showing in right top coner | complete
17 | 2025-03-17 | DashBoard | Manager View | Server issue | complete
18 | 2025-03-17 | DashBoard | executive view | Server issue | complete
19 | 2025-03-17 | DashBoard | Capacity Planing | server issue | complete
20 | 2025-03-17 | reports | Analytics | Server issue | complete
21 | 2025-03-17 | reports | Schedule | Failed to schedule report "API is not working" | complete
22 | 2025-03-17 | Template | Add template | checklists items "+" icon is not working | complete
23 | 2025-03-17 | Template | Add template | Could not validate credentials "API is not working" | complete
24 | 2025-03-17 | Automation | add automation | Failed to save rule. Please try again "Server not working" | complete
25 | 2025-03-17 | AI | New Chat | Button is not working | complete
26 | 2025-03-17 | Organisation | Organisation | Unexpected token '<', "<!DOCTYPE "... is not valid JSON | pending
27 | 2025-03-17 | Approvals | pending | Failed to fetch /users/pending?status_filter=pending | pending
28 | 2025-03-17 | Approvals | Approved | Failed to fetch /users/pending?status_filter=approved | pending
29 | 2025-03-17 | Approvals | Rejected | Failed to fetch /users/pending?status_filter=Rejected | pending
30 | 2025-03-17 | Approvals | Suspened | Failed to fetch /users/pending?status_filter=Suspened | pending
31 | 2025-03-17 | Settings | Security | Two-Factor Authentication | pending
32 | 2025-03-17 | settings | Privacy | Formating of Manage your GDPR and data privacy settings | pending
33 | 2025-03-17 | My Expenses | Date | Date property is not working | complete
34 | 2025-03-17 | My Expenses | Add expenses | "+" two icon | complete
35 | 2025-03-17 | My time | My time | Server issue | complete

## Akshat
# | Date | Module | Screen | Issue | Status | Issue Type
1 | 2026-03-19 | Dashboard | HomeScreen | Height of Recent activity box should be equal to "My task status" box's Height | Pending | UI
2 | 2026-03-19 | Dashboard | Homesceen | Task is shown that its added bot not shown in the list | Pending | Functional
3 | 2026-03-19 | Tasks | My Tasks | "My task" Heading and "add task" button are repeating 2 times | Pending | UI
4 | 2026-03-19 | Tasks | My tasks | Filters are not working | Pending | Functional
5 | 2026-03-19 | Tasks | My tasks> add Tasks | Extra Text is given "From Template te4et (Copy)" | Pending | UI
6 | 2026-03-19 | Tasks | My tasks | We cannot change status by clicking on the the "Status" Token in the list or details box. | Pending | UI
7 | 2026-03-19 | All | - | Cannot see the "Profile Options" when we hover the profile photo of a person. (Same as we get in MS Teams) | Pending | UI
8 | 2026-03-19 | Tasks | My Tasks> View Details | Cannot add comment in details page of Tasks | Pending | Functional
9 | 2026-03-19 | Projects | My Projects> Add Projects | When we attempt to add project then we get "Failed to fetch /api/projects" | Pending | Functional
10 | 2026-03-19 | All | - | When we switch between diff screens then the loading time is too long. (Usually doesn't load") | Pending | Performance
11 | 2026-03-19 | Tasks | My Tasks | Share button is not working | Pending | Functional
12 | 2026-03-20 | Dashboard | Home | In Recent Activity box we should be able to open it up as overlay when we click on it bcoz the message can be long | Pending | UI
13 | 2026-03-20 | Dashboard | Home | When we click on our profile icon on top right, the "profile" option not working. | Pending | Functional
14 | 2026-03-20 | Dashboard | Home | When we click on "This Month" named filter for changing the data on dashboard then its changing the data but not the label | Pending | Functional
15 | 2026-03-20 | Dashboard | Home | When we click on "This Month" named filter, we cannot see custom date variation in it. | Pending | Functional
16 | 2026-03-20 | Dashboard | Home | In my "Task Status" on right lower corner, "view my time" is not working | Pending | Functional
17 | 2026-03-20 | Dashboard | Home | Search Bar not working | Pending | Functional
18 | 2026-03-20 | Dashboard | Home | When we click on View All Notifications, then its recommended to make it as overlay | Pending | UI
19 | 2026-03-20 | Dashboard | Home > All Notifications | New Rule cannot be added | Pending | Functional
20 | 2026-03-20 | Dashboard | Home | No data is shown in "Upcoming Deadlines", when we already have tasks | Pending | Functional
21 | 2026-03-20 | Dashboard | Home | No data is shown in "My Task's Status" | Pending | Functional
22 | 2026-03-20 | Dashboard | Home > All Tasks | In dashboard, its only one task, despite being any number of tasks in the actual list.( This goes same for Due, completed& Overdue Tasks | Pending | Functional
23 | 2026-03-20 | Departments | Departments listing page | Filter is not working | Pending | Functional
24 | 2026-03-20 | Departments | Departments > Details Page | View Details should be an Overlay to make it consistent overall | Pending | UI
25 | 2026-03-20 | Departments | Departments > Edit info | Missing sections to edit department info + inconsistent to design | Pending | Functional
26 | 2026-03-23 | Dashboard | Home | In my task's Status box, play button is not working | Pending | Functional
27 | 2026-03-23 | Departments | Departments listing page | When we go in view members, we dont have an option to find add members | Pending | UI
28 | 2026-03-23 | Departments | Departments listing page | When we go in view projects, we dont have an option to find add projects | Pending | UI
29 | 2026-03-23 | Departments | Departments listing page | The info in "Department details" and "Department Edit" screen is different. (Edit department has missing options). | Pending | Functional
30 | 2026-03-23 | Departments | Departments > Add Department | Less input fields to add department. | Pending | Functional
31 | 2026-03-23 | Clients | Clients listing page | Filters are not working | Pending | Functional
32 | 2026-03-23 | Departments | Departments listing page | Multiple Departments are selected, but "export" option is missing | Pending | Functional
33 | 2026-03-23 | Clients | Clients> Details | View details should be in a overlay format for consistency | Pending | UI
34 | 2026-03-23 | Clients | Clients> Related Projects | In related projects overlay, "add project" button is not working. | Pending | Functional
35 | 2026-03-23 | Clients | Clients> Add Clients | In add clients overlay, we have CTA "Send to manager for approval".But client is added instantly. | Pending | UI/ Functional
36 | 2026-03-23 | Clients | Clients listing page | When we select multiple clients, then the "export selected" and "delete selected" dont work. | Pending | Functional
37 | 2026-03-23 | Projects | Projects> Add Projects | We can select "expected end date" before "start date which should not be thier. | Pending | Functional
38 | 2026-03-23 | Employee | Employee> Add Employee | When we try add a employee, we cannot see the list of departments. | Pending | Functional
39 | 2026-03-23 | Employee | Employee> Add Employee | The input options are less for adding a employee | Pending | UI
40 | 2026-03-23 | Employee | Employee> Add Employee | Employee cant be added. | Pending | Functional
41 | 2026-03-23 | Employee | Emplyee listing page. | Filters only occur when we hover over the filter and its difficult to select them | Pending | UI/ Functional
42 | 2026-03-23 | Workspace | Workspace> Workspace Listing page | Workspace "private" tag remains constant. | Pending | Functional
43 | 2026-03-23 | Workspace | Workspace> Add members | Members cant be added by name or any other id | Pending | Functional
44 | 2026-03-23 | Workspace | Workspace> Add members | We can remove admin also in it, which should not be thier. | Pending | Functional
45 | 2026-03-23 | Workspace | Workspace listing page | No warning overlay, when we delete a workspace. | Pending | Functional
46 | 2026-03-23 | Reports | Analytics | Section not working. Show ing error: "Failed to fetch /api/reports/task-aging" | Pending | Functional
47 | 2026-03-23 | Reports | Scheduled Reports | No change of state when clicked on "Run" | Pending | Functional
48 | 2026-03-23 | Reports | Scheduled Reports | No warning message when report is deleted. | Pending | UI
49 | 2026-03-23 | Reports | Scheduled Reports > Schedule Report | When clicked on "Schedule Report", the input options in the overlay are not self explainatory | Pending | UI
50 | 2026-03-23 | Templates | Task Listing Page | Can't reuse the task templates. (No CTA or option to do it) | Pending | Functional
51 | 2026-03-23 | Templates | Task Listing Page | it is not following the design pattern of the platform, making it confusing | Pending | UI
52 | 2026-03-23 | AI | AI Chat Section | "AI is not configured. Please set up the Gemini API key." | Pending | Functional
53 | 2026-03-23 | Support | Support | Read Status & Date filter not working. | Pending | Functional
54 | 2026-03-23 | Organisations | Organisations | Option to register organization is missing. | Pending | Functional
55 | 2026-03-23 | My Time | My Time | This Section is not loading | Pending | Functional
56 | 2026-03-23 | My Expense | My Expense listing page | Cannot change status when clicked on the "Status token" in the list | Pending | UI
57 | 2026-03-23 | My Expense | My Expense> Add Expense | Cannot select a project | Pending | Functional